Project Planning Phase

SpendWise Money Management Web App

| Date | 10 March 2026 |
| --- | --- |
| Team ID | 69a6aac0f713ea4f3da5604d |
| Project Name | SpendWise |
| Maximum Marks | 5 Marks |

Product Backlog, Sprint Schedule, and Estimation (4 Marks)

| Sprint | Functional Requirement (Epic) | User Story Number | User Story / Task | Story Points | Priority | Team Members |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | Project Setup | USN-1 | Set up Node.js project, install dependencies, and create basic folder structure | 5 | High | Devansh |
| Sprint-1 | Database Connection | USN-2 | Connect MongoDB using Mongoose and configure environment variables | 5 | High | Devansh |
| Sprint-1 | Server Setup | USN-3 | Create Express server and test basic API route | 4 | High | Devansh |
| Sprint-2 | User Authentication | USN-4 | Create User model and implement Register API | 6 | High | Devansh |
| Sprint-2 | User Authentication | USN-5 | Implement Login API with JWT token generation | 6 | High | Devansh |
| Sprint-2 | Security | USN-6 | Create JWT middleware to protect routes | 5 | High | Devansh |
| Sprint-3 | Expense Management | USN-7 | Create expense model and API to add new expense record (Create) | 5 | High | Devansh |
| Sprint-3 | Expense Management | USN-8 | Implement API to fetch user expense records with filtering (Read) | 5 | High | Devansh |
| Sprint-3 | Expense Management | USN-9 | Implement API to update expense record (Update) | 5 | Medium | Devansh |
| Sprint-3 | Expense Management | USN-10 | Implement API to delete expense record (Delete) | 5 | Medium | Devansh |
| Sprint-4 | Budget Management | USN-11 | Create budget model and implement budget creation API | 6 | High | Devansh |
| Sprint-4 | Budget Management | USN-12 | Implement budget tracking and spending alerts API | 7 | High | Devansh |
| Sprint-5 | Analytics & Reports | USN-13 | Implement expense analytics and monthly/yearly reports API | 8 | Medium | Devansh |
| Sprint-5 | Analytics & Reports | USN-14 | Create spending category breakdown and trends API | 6 | Medium | Devansh |
| Sprint-6 | Frontend Integration | USN-15 | Develop responsive dashboard UI with expense overview | 8 | High | Devansh |
| Sprint-6 | Frontend Integration | USN-16 | Create expense entry and management forms | 7 | High | Devansh |
| Sprint-7 | Testing & Optimization | USN-17 | Test all APIs using Postman/Thunder Client and perform integration testing | 6 | High | Devansh |
| Sprint-7 | Documentation | USN-18 | Prepare comprehensive README, API documentation, and user guide | 6 | Medium | Devansh |

Project Tracker, Velocity & Burndown Chart (4 Marks)

| Sprint | Total Story Points | Duration | Sprint Start Date | Sprint End Date (Planned) | Story Points Completed (as on Planned End Date) | Sprint Release Date (Actual) |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | 14 | 3 Days | 1 Mar 2025 | 3 Mar 2025 | 14 |  |
| Sprint-2 | 17 | 3 Days | 4 Mar 2025 | 6 Mar 2025 | 17 |  |
| Sprint-3 | 20 | 4 Days | 7 Mar 2025 | 10 Mar 2025 | 20 |  |
| Sprint-4 | 13 | 3 Days | 11 Mar 2025 | 13 Mar 2025 | 13 |  |
| Sprint-5 | 14 | 4 Days | 14 Mar 2025 | 17 Mar 2025 | 14 |  |
| Sprint-6 | 15 | 4 Days | 18 Mar 2025 | 21 Mar 2025 | 15 |  |
| Sprint-7 | 12 | 3 Days | 22 Mar 2025 | 24 Mar 2025 | 12 |  |

Project Overview

SpendWise is a comprehensive money management web application designed to help users track expenses, manage budgets, and gain insights into their spending patterns. The application will feature user authentication, expense tracking, budget management, analytics, and a responsive web interface.

Key Features:

- User Authentication: Secure registration and login system

- Expense Management: Complete CRUD operations for expense tracking

- Budget Management: Budget creation and spending alerts

- Analytics & Reports: Detailed spending analysis and trends

- Responsive UI: User-friendly dashboard and forms

Technology Stack:

- Backend: Node.js, Express.js

- Database: MongoDB with Mongoose

- Authentication: JWT tokens

- Frontend: HTML, CSS, JavaScript (responsive design)

- Testing: Postman/Thunder Client

This project follows an agile development approach with 7 sprints spanning approximately 24 days, ensuring systematic development and thorough testing of all features.